## recommendation
| Authored by David Malawey, 2009 at TMMK Georgetown Kentucky | [10 empty] | AGM |  |  |  | MGR |  |  | A/M
| Reformatted for clean readability, improved excel template to share 2026.05 | [8 empty] | TEMA
TMMK
9A Press Load Monitoring
ULTIMATE GOAL |  |  |  |  | Root Cause Analysis
no strain gauge system installed on presses
Current situation: | [7 empty] | strain gauges read cross talk within columns
|  |  | The load monitoring system on 9A press is not accurate. | [5 empty] | logic does not compensate for 2 slides
|  |  | The system cannot form a measurement at <50% of press load capacity. | [6 empty] | does not gauge which side the load comes from
|  |  | The measurement is based on pressure readings from hydraulic overload protector system. | [7 empty] | only one strain gauge on each column
system is not calibrated for shared columns
max
|  |  |  | useable but innaccurate | Countermeasures
no load measurement
0 load
[6 empty] | Custom strain gauge system | [6 empty] | O | O | O |  | ∆ | ∆ | O
Ideal Situation: | [5 empty] | Calibrate the current system | [6 empty] | X | ∆ | ∆ |  | ∆ | ∆ | ∆
|  |  | Load monitoring system takes accurate measurement through entire range |  |  | Do nothing | [6 empty] | X | X | O |  | O | O | ∆
|  |  | the system does not require frequent maintenance |  |  | Install strain gauge on slides | [6 empty] | ∆ | ∆ | X |  | ∆ | ∆ | ∆
Gap Identified:
accuracy needs improvement
Schedule/Assignments
Problem Break Down
[6 empty] | Details: |  |  |  | Install strain gauge system for shared slides and use special calibration
[10 empty] | ► | Gauges will measure left and right sides of shared columns
[10 empty] | ► | Calibrate gauges simultaneously with load-cell dies
[10 empty] | ► | Install Allen-Bradley HMI to readout peaks
[10 empty] | ► | Cost is $(?????) for material and contractor installation.
Example of installation on shared columns
STAMPING PRESS PLAN VIEW
Target
|  | ► | install/calibrate a system to read out peak tonnage
|  | ► | use system on press lines with column-sharing slides
|  | ► | Tonnage reads a number that matches same dies tonnage on other machines (accurate)
|  | ► | Tonnage reads consistent numbers (precise)
accurate
precise
maintenance
cost
simple install
OVERALL
reported load (desired)
operating load

## notes
Compiled Notes for A3 Problem Solving on Stamping Press
Notes from my internship in 2009 in kentucky, having 3-4 months experience in stamping department, as an exercise in Toyota's Problem Solving Methods
Reformatted in 2026.05 for readability & sharing online. This is the engineer's first attempt at an A3, with 2.5 years of study in Mech Eng. degree.
Problem Identification
Problem
Modular transfer press load monitor is inaccurate
OCY14Z
Target setting
Targets
| ► | useable below 50% of press tonnage
| ► | accurate tonnage reading
| ► | not expensive
| ► | little maintenance required
Brainstorm Ideas
Pin cushion pressure gauge monitors pressure on pin cushion accurately.
| ► | the pressure gauge for the overload system is already very appropriate for it's application.
| ► | the problem does not lie in the sensor but in the hydraulic system- it is not accurate enough
Strain gauges could be added to the slide
| ► | attachment (welding, tapping, etc) could possibly damage plungers
| ► | wires from strain gauges will be easily damaged.
radio transmitter could transmit signal from atop slide to eliminate wires
Strain gauges could be attached near bearing mounts on shaft?
Strain gauges mounted on the tie rods of each column
| ► | can be calibrated for shared columns?
| ► | two tie rods per column in shared columns?
Actions to Take
My notes did not reach a stage to establish actions but still included the anticipated parties to take action.
|  |  | What | Who | Time schedule:
|  |  | planning | Toyota PE | ?
|  |  | install | Contractor | ?
|  |  | calibration | Both | ?